## Sheet1
Team A, Backlog
Task | Work Unit | Status | Task Details | Start Date | End Date | Person | Estimate | Actual Time | Plan | Result | Obstacles
1 | Administration | N/A | SCRUM Master Duties. | 2014-09-29 | N/A | John | Four Hour - Weekly | Nine Hours | Arrange SCRUM meetings, manage the blacklog and work plan, and designate tasks. | N/A | N/A
2 | Tank Moving off Screen | Completed | Fix the tanks to stay on screen instead of disappearing. | 2014-09-29 | 2014-10-10 | Leah/Mike | Five Hours | Four Hours | Find the code addressing the tanks position during a game restart. From there, the team will implement and test new strategies to ensure the bug is fixed within the first SCRUM cycle. The team will test the bug by using print lines to know its location roughly fifty times. | Achieved | Trouble finding the bugs location. New issues arose that required fixing.
3 | Power on Restart | Completed | Gaurantee tanks are able to shoot and do damage on restarts. | 2014-09-29 | 2014-10-10 | John/Jason | Six Hours | Two Hours | Find the code addressing the power of the tanks during a game restart. The team will correct the code over the next two SCRUM cycles. It will then be tested by printing out the force of the projectiles and repeating fifty times. | Achieved | Like the Tanks Moving Off Screen bug, new issues arose when repairing this bug.
4 | Hersco Bomb | High | Allow for the bomb to hit the ground so the players turn can end. | 2014-10-13 | N/A | John/Jason/Mike | Nine Hours | Twelve Hours | Previously the Space Bar bug. A new plan will be created at the beginning of the next cycle. | Re-Logged (Second Time) | Thought to be a different bug at first, now it was found to have to do with the Hersco Bomb ammunition. The problem is hard to locate. Afer implementing bug fixes, there is one situation where it persists.
5 | Document Code | High | Comment code to the teams detailed rubric. | 2014-09-29 | N/A | John/Jason/Leah/ Mike | Ten Hours | Six and A Half Hours | Continously update the code with comments, documenting the function of certain operations. This will be done throughout the entire project and will match a rubric the team designed. | N/A | Sorting through messy code.
6 | Missed Turns | Completed | Gaurantee turns will switch between players without skipping. | 2014-10-13 | 2014-10-24 | Jason/John/Mike | Three Hours | Four Hours | The team will search the code and implement fixes to guarentee no players turn is missed. This will be done by locating the code, then try various methods to figure out how to make it fully operational. | Achieved | N/A
7 | Help/Tutorial | Completed | Make the Help/Tutorial more clear and useful. | 2014-10-27 | 2014-11-07 | Leah | Three Hours | Three Hours | Clean up the Help/Tutorial screen to make it more user friendly and accurate. | Achieved | N/A
8 | Screen Transition | Medium | Smooth the transition between screens. | N/A | N/A | 3 members (tbd) | N/A | N/A | N/A | N/A | N/A
9 | Music Overlap | Medium | Make sure the music only plays when it should be playing. | 2014-10-27 | N/A | Jason | Two Hours | Three Hours | Check and ensure audio plays when it is suppose to and no awkward transitions exist. | Re-Logged | Hard to find any presence of music overlap as previously discovered.Bug has to do with screen transitions. Added to backlog.
10 | Buttons | Low | Fix broken buttons. | N/A | N/A | 1 member (tbd) | N/A | N/A | N/A | N/A | N/A
11 | Frozen Game | Low | Prevent the game from locking up and forcing a restart. | 2014-10-13 | N/A | Leah/Mike | Five Hours | Five Hours | This bug does not occur often, but the team will search for any reasons of why the game would randomly freeze. It is a high annoyance, but not game breaking. The team will try various methods to fix this bug. | Re-Prioritized | Could not locate any issues, thus it was tested and proven to be no issue or something to be looked upon later.
12 | Blank Transparent Win Screen | Low | Remove or improve the win screen. | N/A | N/A | 1 member (tbd) | N/A | N/A | N/A | N/A | N/A
13 | Testing | N/A | Test bug fixes and enhancements implementations. | 2014-09-29 | N/A | Leah | Thirteen Hours | Eleven Hours | Testing will encompass going through various testing cycles to ensure all bugs are fixed. It will also check for new bugs. Println() will be very useful in testing. | N/A | Frozen Game bug was not evident and thus hard to test (Cycle 2). Hersco Bomb failed 13 times out of 50 (Cycle 3).