## Sheet1
Team A, SCRUM Cycle 4, 11/21/14 Version
Task | Work Unit | Status | Task Details | Start Date | End Date | Person | Estimate | Actual Time | Plan | Result | Obstacles
1 | Administration - Includes Meetings | N/A | SCRUM Master Duties. | 2014-11-10 | 2014-11-21 | John | Four Hours | Four Hours | Arrange SCRUM meetings, manage the blacklog and work plan, and designate tasks. | Completed | N/A
2 | Hersco Bomb | High | Allow for the bomb to hit the ground so the players turn can end. | 2014-11-10 | 2014-11-21 | John/Jason/Mike | Four Hours | Four Hours | Polish off the Hersco Bomb fix. | Not Reached | Tweaks were implemented to improve the bug but overall the team could not completely fix it.
z | New Weapon | High | Remove the Joker Bomb and implement a new weapon feature. | 2014-11-10 | 2014-11-21 | John/Jason/Mike/ Leah | Six Hours | Seven Hours | Create and implement a new weapon. | Completed | Wanted to implement more to the new weapon, but could not do it within the time of the cycle.
4 | Document Code | High | Comment code to the teams detailed rubric. | 2014-11-10 | 2014-11-21 | John/Jason/Leah/ Mike | Two Hours | Three Hours | Continously update the code with comments, documenting the function of certain operations. This will be done throughout the entire project and will match a rubric the team designed. | Completed | N/A
5 | Music Overlap | Medium | Make sure the music only plays when it should be playing. | 2014-11-10 | 2014-11-21 | Jason | Three Hours | Three Hours | Check and ensure audio plays when it is suppose to and no awkward transitions exist. | Completed | Rare situations occur where the bug is found, but no implementation rendered a fix. The bug being so minor has let the team decide it is no concern.
6 | Screen Transition | Medium | Smooth the transition between screens. | 2014-11-10 | 2014-11-21 | John/Jason | Two Hours | One Hour | Check if there is anyway to smooth the transitions between screens. | Completed | Nothing found.
7 | Buttons | Low | Fix broken buttons. | 2014-11-10 | 2014-11-21 | Leah | One Hour | One Hour | Ensure all buttons work. | Completed | N/A
8 | Frozen Game | Low | Prevent the game from locking up and forcing a restart. | 2014-11-10 | 2014-11-21 | Leah | One Hour | One Hour | This bug does not occur often, but the team will search for any reasons of why the game would randomly freeze. It is a high annoyance, but not game breaking. The team will try various methods to fix this bug. | Completed | N/A
9 | Blank Transparent Win Screen | Low | Remove or improve the win screen. | 2014-11-10 | 2014-11-21 | Mike/John | Two Hours | One Hour | Remove or improve the blank win screen. | Completed | N/A
10 | Testing | N/A | Test bug fixes and enhancements implementations. | 2014-11-10 | 2014-11-21 | Leah | Five Hours | Seven Hours | Testing will encompass going through various testing cycles to ensure all bugs are fixed. It will also check for new bugs. Println() will be very useful in testing. | Completed | N/A
[7 empty] | Total: Thirty Hours | Total: Thirty-Two Hours